## Report
From |  | 2025-03-02 | To | 2025-03-09
Projects |  | Ink Link
Time Zone |  | Current User
Generated on |  | 2025-03-09T22:58:40-04:00
Report Time Format |  | Hours
Work logs Time Format |  | Hours
Work Log Author | Total Work Log Author
Boyu Ren | 3
Derek Gonzalez | 8
Jacob Manhardt | 7.33
Runnan Li | 6.67
Sebastian Barahona-Gonzalez | 7.33
Total | 32.33

## Work logs
Author | Issue | Issue Summary | Work log started | Work log created | Work log time zone | Time spent | Work log comment
Boyu Ren | IL-7 | Chat service | 2025-03-09 19:32 | 2025-03-09 22:32 | America/New_York | 3
Derek Gonzalez | IL-117 | Create an artist locator | 2025-03-04 22:21 | 2025-03-09 22:30 | America/New_York | 8
Jacob Manhardt | IL-98 | Design and prototype main gallery page | 2025-03-02 14:00 | 2025-03-02 17:57 | America/New_York | 3
Jacob Manhardt | IL-105 | Sprint Retrospective | 2025-03-02 18:07 | 2025-03-02 18:22 | America/New_York | 0.25 | Whole team
Jacob Manhardt | IL-112 | Previous Spirit Artifacts | 2025-03-03 11:13 | 2025-03-03 11:18 | America/New_York | 0.08
Jacob Manhardt | IL-116 | Create the html for the gallery page | 2025-03-04 11:20 | 2025-03-04 12:21 | America/New_York | 1 | set up the hero page and the gallery. working on scroll snapping next
Jacob Manhardt | IL-116 | Create the html for the gallery page | 2025-03-09 16:30 | 2025-03-09 22:22 | America/New_York | 3
Runnan Li | IL-88 | SCRUM | 2025-03-04 19:59 | 2025-03-04 20:10 | America/New_York | 0.17 | Everyone attended the meeting and talked about the process each member made.
Runnan Li | IL-90 | SCRUM 2 | 2025-03-06 20:05 | 2025-03-06 20:26 | America/New_York | 0.33 | Talk about our progress and decide whether we are going to finish sprint 5 this Sunday and start sprint 6 so we can earn extra points
Runnan Li | IL-114 | Create HTML For profile page | 2025-03-07 19:31 | 2025-03-09 22:31 | America/New_York | 6
Runnan Li | IL-86 | Sprint Retrospective | 2025-03-09 22:14 | 2025-03-09 22:24 | America/New_York | 0.17 | talk about improves and sustainment
Sebastian Barahona-Gonzalez | IL-110 | Create the Amazon database | 2025-03-09 18:30 | 2025-03-09 22:30 | America/New_York | 4
Sebastian Barahona-Gonzalez | IL-113 | Find how to get images into the site and populate the gallery | 2025-03-09 19:30 | 2025-03-09 22:30 | America/New_York | 3
Sebastian Barahona-Gonzalez | IL-108 | Create new GitHub | 2025-03-09 22:09 | 2025-03-09 22:29 | America/New_York | 0.33